## Cover Page
IoT Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today | 2025-07-29
Project Team Name | SmartGuardian
Project Topic | IoT-Based Environmental Monitoring and Fire-Gas Alert System Using ESP8266
Task |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[7 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[7 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
Research components and design plan |  |  |  | Hà Trung Thành |  | Done
Integrate sensors with ESP8266 |  |  |  | Hà Trung Thành |  | Done
Develop Node-RED dashboard |  |  |  | Phạm Thu Hà |  | Done
Configure MQTT and test communication |  |  |  | Phạm Thu Hà |  | Done
Setup and connect InfluxDB |  |  |  | Nguyễn Tuấn Kiệt |  | Done | bar: 2021-11-01 to 2021-11-08; 2021-11-14 to 2021-11-17; 2021-11-19 to 2021-11-20
Data analysis and formatting |  |  |  | Nguyễn Tuấn Kiệt |  | Done | bar: 2021-11-01 to 2021-11-06; 2021-11-14 to 2021-11-15; 2021-11-19 to 2021-11-20
LCD display & buzzer alert system |  |  |  | Phạm Thu Hà |  | Done | bar: 2021-11-01 to 2021-11-08; 2021-11-14 to 2021-11-17; 2021-11-19 to 2021-11-20
Final testing & documentation |  |  |  | Hà Trung Thành |  | Done | bar: 2021-11-01 to 2021-11-06; 2021-11-14 to 2021-11-15; 2021-11-19 to 2021-11-20
Build circuit on breadboard |  |  |  | Phạm Thu Hà |  | Done
Design flowchart and block diagram |  |  |  | Hà Trung Thành |  | Done
Create presentation slides |  |  |  | Nguyễn Duy Phúc |  | Done | bar: 2021-11-01 to 2021-11-08; 2021-11-14 to 2021-11-17; 2021-11-19 to 2021-11-20
System demo preparation and dry run |  |  |  | Phạm Thu Hà |  | Done | bar: 2021-11-01 to 2021-11-06; 2021-11-14 to 2021-11-15; 2021-11-19 to 2021-11-20
Write project report (English) |  |  |  | Nguyễn Duy Phúc |  | Done
Translate report to Vietnamese |  |  |  | Phạm Thu Hà |  | Done
System deployment test (simulated environment) |  |  |  | Phạm Thu Hà |  | Done